## Slide 1
BOARD UPDATE · OCTOBER 2026
Pilot contracted. Security work is the critical path.
Confidential · figures labelled sample until audited

## Slide 2
NUMBERS VS PLAN
Contracted ARR
$0
Pilot fee billed as services
Cash on hand
$14.2k
◌ Sample
Monthly burn
$565
On plan
Pipeline
3
Institutions in discovery

## Slide 3
VANDERBILT PILOT
Signed. Start date depends on four security deliverables.
◆ DPA / FERPA addendum
Signed
… HECVAT Full
70% drafted
… SAML SSO
Built, untested with IdP
○ Cyber + E&O insurance
Quotes requested

## Slide 4
PRODUCT THIS PERIOD
Registrar console: readiness + holds
Course Studio for faculty
Security hardening migration + tests
Privacy center for students
registrar console screenshot

## Slide 5
TOP RISKS
Risk
Level
Mitigation
Solo founder bandwidth
! High
Contract security reviewer; hire founding engineer
Insurance before go-live
! High
Two brokers engaged; bind by Nov 15
SIS data quality
? Medium
Data readiness checklist with IT

## Slide 6
CASH AND RUNWAY
Runway is 25 months at current burn; setup spend lands before go-live.
Setup budget base case $12,430 (range $4,873–$19,910). Run-rate $565/month. ◌ Sample figures from the finance model.

## Slide 7
WHAT I NEED FROM YOU
Intro to a higher-ed insurance broker
Reviewer for the HECVAT before submission
Two warm intros to registrars outside Tennessee

## Slide 8
NEXT PERIOD
Submit HECVAT Full and ACR draft
SSO tested with Vanderbilt's IdP
Insurance bound; go/no-go set